## Sheet1
Bug Number | Description | Bug Date | Raised By | Category | Status | Siviority | Priority | Comments
1 | It is accepting positive value and throwing error . It means ,if we enter valid data it should not throw error, but it is throwing error | 2016-07-26 | Tulasi | Software | closed |  |  | The bug is not clear, please mention exact steps to reproduce which will help me in fixing the issue
2 | patient window is accepting complete data with negative UID value also | 2016-07-26 | Tulasi | Software | closed
3 | UID is accepting zero value | 2016-07-26 | Tulasi | Software | closed
4 | UID is accepting Special Characters | 2016-07-26 | Tulasi | Software | closed
5 | UID is accepting decimal values | 2016-07-26 | Tulasi | Software | closed
6 | UID is accepting characters | 2016-07-26 | Ramesh | Software | closed
7 | UID is accepting greater than 9999999999 | 2016-07-26 | Ramesh | Software | closed
8 | DOB field is accepting less than 1866 | 2016-07-28 | Tulasi | Software | closed | Critical |  |  | Name | Bug Status | Siviority | Priority | Category
9 | DOB field is accepting greater than today | 2016-07-28 | Tulasi | Software | closed | Critical |  | IT IS NOT SHOWING ANY ERROR FOR SPECIFIC FIELD , FOR EVERY FIELD VALIDATION IT IS SHOWING ERROR AS DOB FIELD | Tulasi | open | Critical | High | Software
10 | DOB field is not accepting date | 2016-07-28 | Tulasi | Software | fixed | Critical |  | This bug is fixed please validate and close the bug. Thanks Rameshbabu | Ramesh | assigned | Major | Medium | Requirement
11 | Age field is accepting more than 150 years | 2016-07-28 | Tulasi | Software | closed | Critical |  |  |  | fixed | Minor | Low | TestSpec
12 | Age field is accepting negative values also | 2016-07-28 | Tulasi | Software | closed | Critical |  |  |  | reopen
13 | Sex field is accepting any characters | 2016-07-28 | Tulasi | Software | closed | Critical |  |  |  | closed
14 | Sex field is accepting special characters and numbers also | 2016-07-28 | Tulasi | Software | closed | Critical |  |  |  | terminated
15 | Height field is accepting 5.6 and 5'6" also | 2016-07-28 | Tulasi | Software | closed | Major
16 | Height field is accepting special characters and characters | 2016-07-28 | Tulasi | Software | closed | Major
17 | Height field are accepting more than 9 feet | 2016-07-28 | Tulasi | Software | closed | Major
18 | Height field are accepting more than 12 inches | 2016-07-28 | Tulasi | Software | closed | Major
19 | Weight field is accepting more than required weight | 2016-07-31 | Tulasi | Software | closed | Major
20 | Weight field is accepting characters, special characters and negative values | 2016-07-31 | Tulasi | Software | closed | Major
21 | Address field is accepting negative numbers | 2016-07-31 | Tulasi | Requirement | terminated | Critical |  | Not a valid bug, please reevaluate this bug and before raising the bug talk to the developer and also get more clarity on FS document.
22 | Aadhaar No is accepting more than 12 digits | 2016-07-31 | Tulasi | Requirement | closed | Critical
23 | Aadhaar No is accepting characters and special characters | 2016-07-31 | Tulasi | Software | closed | Critical
24 | changes made in DOB format is not identifying BirthDay field | 2016-08-06 | Tulasi | Software | closed | Critical
25 | cannot identify which field but while running application it is showing error message input string is not in correct format | 2016-08-07 | Tulasi | Software | closed | Critical